## Slide 1: Electrical Competency Ruler Pilot: Revised Timeline
Draft for Steering Committee, 26 Oct 2026 | Pod 4: Capability & Talent Strength
STEP 1
Secure PETRONAS Electrical ruler
Initial discussion held. Partial base ruler shared; full release pending PETRONAS management approval.
Ongoing
Now – 6 Nov
STEP 2
Customise ruler to Gentari's needs
Map the ruler to Gentari electrical roles, levels and business requirements.
Upcoming
9 Nov – 4 Dec
STEP 3
Review & refine the customised ruler
With PETRONAS specialists and internal focal; finalise the pilot version.
Upcoming
7 Dec – 15 Jan
STEP 4
Apply ruler to Electrical pilot group
Assess pilot participants and identify capability gaps.
Upcoming
18 Jan – 26 Feb
STEP 5
Link gaps to Individual Development Plans
Translate identified gaps into IDP actions with managers.
Upcoming
1 – 26 Mar
STEP 6
Review pilot outcomes
Pilot report and recommendation to SCo on broader adoption.
Upcoming
Apr 2027 (SCo TBC)
Critical path: Steps 2 to 6 depend on PETRONAS management approval in Step 1. Each week of delay moves every downstream step by a week. Target dates are proposed for SCo discussion.
Notes: Revised from the earlier plan, which showed the customisation step as completed. In practice only an initial discussion with the PETRONAS Principal (Electrical) has happened: PETRONAS shared part of its broad-based electrical ruler and the rest is awaiting PETRONAS management approval. Dates after Step 1 are proposals and shift one-for-one with the approval date.

## Slide 2: Pilot runs to Apr 2027, gated by PETRONAS approval
Oct
Nov
Dec
Jan
Feb
Mar
Apr
1 Secure PETRONAS ruler
Now – 6 Nov
2 Customise ruler
9 Nov – 4 Dec
3 Review & refine
7 Dec – 15 Jan
+ Identify & brief pilot group
16 Nov – 18 Dec
4 Apply ruler, identify gaps
18 Jan – 26 Feb
5 Link gaps to IDPs
1 – 26 Mar
6 Review pilot outcomes
Apr (SCo TBC)
SCo 26 Oct
Ongoing
Upcoming
Enabling activity
Asks of the SCo
Endorse the revised timeline and reset the Stage 3 gates (pilot report, handover, showcase)
Sponsor support to expedite PETRONAS management approval of the ruler release
Confirm the pilot group and a named Electrical internal focal
Agree a fallback if the full ruler is not released: proceed with the shared portion, or consider consultancy support
Key risks and mitigation
Approval delay slips Steps 2 to 6 one-for-one: start with the portion already shared
Year-end leave overlaps Step 3: book PETRONAS specialist sessions by Nov
Access for staff outside the PETRONAS email domain: agree the route with ICT early
Notes: Gantt is built from proposed windows. Dates move with the PETRONAS approval date in Step 1. The enabling row (identify and brief pilot group) runs in parallel with Steps 2 and 3 so the group is ready when the ruler is finalised. The earlier lifecycle plan had pilot report approval at an estimated 27 Oct, handover at 18 Nov and the One Gentari showcase on 2 Dec; these need to be reset against this timeline.